## Cover Page
AI CODE REVIEWER
Agile Project Documentation
PROJECT DETAILS
Project Name | Development of AI-Driven Code Reviewer
Internship | Infosys Springboard Virtual Internship 6.0
Batch / Group | Batch 13 — Group 1
Methodology | Agile / Scrum
Total Sprints | 4 Sprints (2 weeks each)
Start Date | 02 February 2026
End Date | 29 March 2026
Live URL | https://ai-code-reviewer-gold-moon.reflex.run/
Tech Stack | Python, Reflex, AST, Groq API (LLaMA 3.1 8B), LangChain, SQLModel
DOCUMENT INDEX
Sheet Name | Description | No. of Records
Product Backlog | User Stories with MOSCOW priority, assignee and status | 16 User Stories
Sprint Backlog | 4 Sprints with tasks, effort estimates and day-wise tracking | 28 Tasks
Stand Up Meeting | Daily standup logs — impediments and actions taken | 10 Standup Logs
Retrospection | Sprint retrospectives — Start / Stop / Continue doing | 4 Sprint Reviews
Defect Tracker | Bugs found during testing with fix details and status | 10 Defects
Unit Test Plan | Test cases covering all modules with expected vs actual results | 15 Test Cases
Infosys Springboard Virtual Internship 6.0 ¦ Batch 13, Group 1 ¦ 2026

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | As a student, I can open the AI Code Reviewer web app at the live URL (ai-code-reviewer-gold-moon.reflex.run) | Must Have | None | All Team | Done
1 | 1 | US-02 | As a user, I see a professional homepage (hero.py) with "Review Your Code with AI" headline, "Start Reviewing" and "Try Demo" buttons | Must Have | None | Frontend Dev | Done
1 | 1 | US-03 | As a user, I can navigate between Home, Analyze, History, and About pages using the navbar (navbar.py) | Must Have | US-02 | Frontend Dev | Done
1 | 1 | US-04 | As a developer, the Reflex project structure is set up with components/, state.py, models.py, alembic for DB migrations | Must Have | None | All Team | Done
2 | 2 | US-05 | As a student, I can paste my Python code into the Analyze page (analyze.py) code editor and click "Analyze Code" | Must Have | US-03 | Frontend Dev | Done
2 | 2 | US-06 | As a student, my code is parsed using AST via code_parser.py to extract structure before analysis | Must Have | US-05 | Backend Dev | Done
2 | 2 | US-07 | As a student, the error_detector.py module detects unused variables and unused imports (e.g. unused variable x, unused import os) | Must Have | US-06 | Backend Dev | Done
2 | 2 | US-08 | As a student, the code_analyzer.py module gives me a Score (e.g. 90/100) and lists all Issues Found | Must Have | US-07 | AI Dev | Done
2 | 2 | US-09 | As a student, the ai_suggester.py calls GPT/LLM API and returns AI Suggestions: Errors, Improvements, Time Complexity, Space Complexity, PEP8 Issues | Must Have | US-08 | AI Dev | Done
3 | 3 | US-10 | As a student, I see side-by-side "Your Code" (blue panel) vs "Corrected Code" (green panel) with a Copy button after analysis | Must Have | US-09 | Frontend Dev | Done
3 | 3 | US-11 | As a student, all my previous code analyses are saved to the database (models.py + alembic) and visible in the History page (history.py) | Must Have | US-08 | Backend Dev | Done
3 | 3 | US-12 | As a user, I can click any history entry to expand it and see full Score, Issues, AI Suggestions, and an "Edit in Analyzer" button | Should Have | US-11 | Frontend Dev | Done
3 | 3 | US-13 | As a user, the About page (about.py) shows Our Mission, How It Works (3 steps), Technologies Used (Python, Reflex, AI/LLM), and Contact section | Should Have | None | Frontend Dev | Done
4 | 4 | US-14 | As a user, the footer (footer.py) shows AI Code Reviewer branding, Product links (Analyze, About, History), Connect links (GitHub, LinkedIn, YouTube, Email) | Could Have | US-02 | Frontend Dev | Done
4 | 4 | US-15 | As a user, the app is fully responsive — homepage, analyze page, history page all work on mobile and desktop | Should Have | US-02 | Frontend Dev | Done
4 | 4 | US-16 | As a team, we present a polished PPT covering Problem Statement, Solution, Architecture, Demo screenshots, and Results | Must Have | None | All Team | To Do

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 79 | 4 | 6 | 8 | 11 | 10 | 10 | 8 | 7 | 6 | 4 | 2 | 1 | 4 | 0
SPRINT 1 BACKLOG
Sprint 1 — Project Setup & UI Foundation ¦ 02 Feb – 15 Feb 2026
US-01 | T-01 | Create GitHub repo, set up Reflex project structure (AI_CODE_REVIEWER folder, venv, .env, requirements.txt, alembic.ini) | 02-Feb | 03-Feb | All Team | Setup | Done | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-02 | Configure alembic for database migrations (models.py with SQLModel) | 03-Feb | 05-Feb | Backend Dev | Setup | Done | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-03 | Build navbar.py component — Logo, Home, Analyze, History, About nav links with active state | 04-Feb | 06-Feb | Frontend Dev | Development | Done | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-04 | Build hero.py — Full-screen hero section with "Review Your Code with AI" heading, Start Reviewing + Try Demo buttons | 05-Feb | 09-Feb | Frontend Dev | Development | Done | 4 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-05 | Deploy Reflex app to Reflex Cloud — live at ai-code-reviewer-gold-moon.reflex.run | 10-Feb | 12-Feb | Backend Dev | Deployment | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US-01 | T-06 | Create __init__.py exports for components/ package | 12-Feb | 13-Feb | Backend Dev | Setup | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
US-04 | T-07 | Sprint 1 Review & Retrospective — demo homepage, check deployment URL | 15-Feb | 15-Feb | All Team | Review | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Sprint 2 — Core Analysis Engine (AST + AI) ¦ 16 Feb – 01 Mar 2026
US-05 | T-08 | Build analyze.py — Code editor textarea, language selector dropdown, Analyze Code button, Score display panel | 16-Feb | 19-Feb | Frontend Dev | Development | Done | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-09 | Implement code_parser.py — Accept Python code input, parse using AST module, extract functions/variables/imports | 18-Feb | 21-Feb | Backend Dev | Development | Done | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-10 | Implement error_detector.py — Detect unused variables (e.g. x=10 never used), unused imports (import os), undefined vars | 19-Feb | 23-Feb | Backend Dev | Development | Done | 4 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-11 | Implement code_analyzer.py — Aggregate errors, compute Score /100, format Issues Found list | 21-Feb | 24-Feb | AI Dev | Development | Done | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-12 | Implement ai_suggester.py — Connect GPT/LLM API, build prompt, return Errors, Improvements, Time Complexity, Space Complexity, PEP8 Issues | 22-Feb | 27-Feb | AI Dev | Development | Done | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0
US-09 | T-13 | Wire state.py — Manage analyze_code() event handler, store result in state, trigger UI re-render | 25-Feb | 28-Feb | Backend Dev | Development | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0
US-05 | T-14 | Sprint 2 Review & Retrospective — demo full analyze flow with Score + AI output | 01-Mar | 01-Mar | All Team | Review | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Sprint 3 — Output, History & DB Integration ¦ 02 Mar – 15 Mar 2026
US-10 | T-15 | Add "Your Code" (blue) vs "Corrected Code" (green) side-by-side panels in analyze.py output section | 02-Mar | 05-Mar | Frontend Dev | Development | Done | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-16 | Add Copy button (📋) for Corrected Code panel — clipboard functionality | 04-Mar | 06-Mar | Frontend Dev | Development | Done | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-17 | Build history.py — Show all previous analyses from DB, each entry shows code snippet preview, Score, timestamp | 05-Mar | 09-Mar | Backend Dev | Development | Done | 4 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-18 | Make history entries expandable — click to show full Score, Issues, AI Suggestions, "Edit in Analyzer" button | 07-Mar | 11-Mar | Frontend Dev | Development | Done | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-13 | T-19 | Build about.py — Our Mission section, How It Works (3 steps: Paste Code, AI Analyzes, Get Suggestions), Technologies (Python, Reflex, AI/LLM), Contact | 09-Mar | 12-Mar | Frontend Dev | Development | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
US-11 | T-20 | Configure models.py + alembic migration — AnalysisHistory table with code, score, issues, suggestions, timestamp columns | 10-Mar | 13-Mar | Backend Dev | Development | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
US-12 | T-21 | Sprint 3 Review & Retrospective — demo history page, about page, corrected code panel | 15-Mar | 15-Mar | All Team | Review | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Sprint 4 — Polish, Testing & Deployment ¦ 16 Mar – 29 Mar 2026
US-14 | T-22 | Build footer.py — Brand logo + tagline, Product links (Analyze, About, History), Connect (GitHub, LinkedIn, YouTube, Email), Follow us icons | 16-Mar | 18-Mar | Frontend Dev | Development | Done | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-23 | Responsive CSS — Test on 375px mobile, 768px tablet, 1280px desktop; fix layout breaks | 17-Mar | 20-Mar | Frontend Dev | Testing | To Do | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-24 | Unit test error_detector.py — test unused var, unused import, empty input, valid code edge cases | 18-Mar | 22-Mar | Backend Dev | Testing | To Do | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-25 | Integration test ai_suggester.py — verify GPT API returns all 5 sections (Errors, Improvements, Time Complexity, Space Complexity, PEP8) | 20-Mar | 24-Mar | AI Dev | Testing | To Do | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-16 | T-26 | Create final PPT — Title, Problem Statement, Solution Architecture, Module walkthrough, UI screenshots, Live Demo link, Results | 21-Mar | 27-Mar | All Team | Documentation | To Do | 5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-01 | T-27 | Final smoke test on live URL — verify all pages, analyze flow, history, copy button work on production | 26-Mar | 28-Mar | All Team | Testing | To Do | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
US-16 | T-28 | Sprint 4 Review + Final Project Demo to Infosys mentors | 29-Mar | 29-Mar | All Team | Review | To Do | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1

## Stand Up Meeting
Sprint | Day | Impediments | Action Taken
1 | Day 2 (03-Feb) | Reflex version conflict — components not rendering | Pinned Reflex==0.4.6 in requirements.txt; all team updated venv
1 | Day 5 (06-Feb) | Navbar active state not highlighting current page | Fixed using rx.State route variable in navbar.py
1 | Day 8 (09-Feb) | Hero.py background image not loading on deployment | Used relative asset path via rx.asset() function
2 | Day 2 (17-Feb) | AST parser throwing AttributeError on lambda functions | Added try-except in code_parser.py; lambdas now skipped gracefully
2 | Day 6 (21-Feb) | error_detector.py missing detection for redefined builtins | Added builtins check using Python builtins module
2 | Day 9 (24-Feb) | GPT API prompt returning inconsistent section format | Rewrote system prompt in ai_suggester.py with strict JSON-like format
3 | Day 3 (04-Mar) | Side-by-side code panels overlapping on 768px screen | Applied CSS grid with 1fr 1fr columns and min-width guard
3 | Day 6 (07-Mar) | Alembic migration failing due to missing nullable field | Added nullable=True to suggestions column in models.py migration
4 | Day 2 (17-Mar) | Copy button not working on Firefox (clipboard API blocked) | Added fallback using document.execCommand for Firefox compatibility
4 | Day 5 (20-Mar) | PPT slide order unclear for final demo flow | Team agreed: Problem → Architecture → Module Demo → Live URL → Results

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 02-Feb-26 | 15-Feb-26 | All Team | Set up virtual environment before first meeting so all members start on same config | Spending 2+ days on Reflex version conflicts and deployment config issues | Daily WhatsApp checkins — helped catch blockers fast | Created shared requirements.txt and setup guide in README.md
2 | 2 | 16-Feb-26 | 01-Mar-26 | All Team | Test GPT API prompts with many code samples before finalizing prompt template | Hardcoding test code in ai_suggester.py instead of using separate test files | Dividing tasks by module (each person owns one .py file) — very efficient | Rewrote ai_suggester.py prompt with strict section headers — consistent output now
3 | 3 | 02-Mar-26 | 15-Mar-26 | All Team | Use alembic revision --autogenerate to create migrations instead of manual edits | Directly editing DB schema without running alembic migration — caused sync errors | Code review on GitHub before merging to main — caught 3 bugs before they went live | Fixed models.py nullable issue; added alembic best-practices to team wiki
4 | 4 | 16-Mar-26 | 29-Mar-26 | All Team | Start PPT and documentation alongside development from Sprint 1 onwards | Leaving final testing and PPT to last sprint — creates time pressure | Live URL testing on multiple browsers — found real bugs not visible in local dev | Will document all modules in README; PPT covers all required sections for demo
5
6
7

## Defect Tracker
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Team | 06-Feb-26 | hero.py: Background hero image not displaying after Reflex Cloud deployment — rx.image path incorrect | Sprint 1 | Frontend Dev | User Interface | Changed to rx.asset("hero_bg.jpg") relative path in hero.py | 07-Feb-26 | Closed | Fixed in hero.py component
2 | QA Team | 07-Feb-26 | navbar.py: Active page link not highlighted — all nav links showing same colour regardless of current route | Sprint 1 | Frontend Dev | User Interface | Used rx.State.router.page.path to detect active route and apply CSS class | 08-Feb-26 | Closed | State-based active link working
3 | QA Team | 17-Feb-26 | code_parser.py: AttributeError crash when parsing lambda expressions (e.g. lambda x: x+1) using ast.walk() | Sprint 2 | Backend Dev | Logical | Wrapped ast.walk() in try-except; added isinstance check to skip lambda nodes | 18-Feb-26 | Closed | Lambda functions now handled gracefully
4 | QA Team | 20-Feb-26 | error_detector.py: Unused import detection failing for "from module import *" wildcard imports | Sprint 2 | Backend Dev | Logical | Added special case handling for ast.ImportFrom with names=['*'] | 21-Feb-26 | Closed | Wildcard import now flagged correctly
5 | QA Team | 23-Feb-26 | ai_suggester.py: GPT API returning plain text instead of structured sections — "Errors:", "Improvements:" headers missing | Sprint 2 | AI Dev | Logical | Rewrote system prompt with explicit section format instructions and added parsing logic | 24-Feb-26 | Closed | Structured output now consistent
6 | QA Team | 25-Feb-26 | code_analyzer.py: Score calculation returning negative values for code with 10+ errors | Sprint 2 | AI Dev | Logical | Added max(0, score) clamp in score calculation logic | 25-Feb-26 | Closed | Score now minimum 0/100
7 | QA Team | 05-Mar-26 | analyze.py: "Your Code" vs "Corrected Code" panels overlapping on 768px tablet screen width | Sprint 3 | Frontend Dev | User Interface | Applied CSS grid layout with responsive breakpoints; panels stack vertically on mobile | 07-Mar-26 | Closed | Responsive layout working on 375px and 768px
8 | QA Team | 07-Mar-26 | models.py: Alembic migration failing — suggestions column not nullable causing IntegrityError on first run | Sprint 3 | Backend Dev | Logical | Set nullable=True on suggestions column in models.py; generated new alembic revision | 08-Mar-26 | Closed | Migration runs cleanly on fresh DB
9 | QA Team | 10-Mar-26 | history.py: Timestamp showing in UTC instead of local IST timezone — confusing for users | Sprint 3 | Backend Dev | Standards | Applied IST offset (+5:30) conversion when storing and displaying timestamps | 11-Mar-26 | Closed | Timestamps now display in IST
10 | QA Team | 18-Mar-26 | footer.py: Copy-to-clipboard (📋) button for Corrected Code not working in Firefox — Clipboard API blocked | Sprint 4 | Frontend Dev | User Interface | Added document.execCommand("copy") fallback for browsers without Clipboard API support | 19-Mar-26 | Closed | Works across Chrome, Firefox, Edge

## Unit Test Plan
Sl: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result
1 | code_parser.py — Valid Python function parse | Call parse() with valid Python function def | Input: "def add(a,b): return a+b" | Returns AST tree object with FunctionDef node; no exception raised | Returns valid AST tree ✅ PASS
2 | code_parser.py — Empty string input | Call parse() with empty string | Input: "" (empty) | Raises ValueError with message "No code provided" | ValueError raised correctly ✅ PASS
3 | code_parser.py — Syntax error code | Call parse() with code missing colon | Input: "if x > 0 print(x)" | Raises SyntaxError with line number in message | SyntaxError detected at line 1 ✅ PASS
4 | error_detector.py — Unused variable detection | Call detect_errors() on code with x=10 never used | Input: "def f(a,b):\n result=a+b\n x=10\n return result" | Returns issue: "Unused variable: x at line 3" | Unused variable x detected ✅ PASS
5 | error_detector.py — Unused import detection | Call detect_errors() on code with unused import os | Input: "import os\ndef f(): return 1" | Returns issue: "Unused import: os at line 1" | Unused import os detected ✅ PASS — matches live app screenshot
6 | error_detector.py — Clean code returns empty list | Call detect_errors() on code with no issues | Input: "def add(a,b): return a+b" | Returns empty issues list [] | Empty list returned ✅ PASS
7 | code_analyzer.py — Score 90/100 for minor issues | Call analyze() on code with 1 unused var + 1 unused import | Input: code from live app demo (import os, x=10 unused) | Returns score=90, issues=["Unused variable: x","Unused import: os"] | Score: 90/100 returned ✅ PASS — verified in live app screenshot
8 | code_analyzer.py — Score 100/100 for clean code | Call analyze() on perfectly clean code | Input: "def add(a,b):\n return a+b\nprint(add(5,3))" | Returns score=100, issues=[] (empty) | Score: 100/100 returned ✅ PASS — verified in history page (10/0 snippet)
9 | code_analyzer.py — Score never goes below 0 | Call analyze() on code with 15+ errors | Input: code with multiple undefined vars, unused imports, bad formatting | Returns score >= 0 (clamped, not negative) | Score: 0/100 returned (not negative) ✅ PASS
10 | ai_suggester.py — Returns all 5 required sections | Call suggest() with code sample | Input: code from live demo (import os + calculate_sum) | Returns dict with keys: Errors, Improvements, Time Complexity, Space Complexity, PEP8 Issues | All 5 sections returned ✅ PASS — verified in Analyze page screenshot
11 | ai_suggester.py — Time complexity analysis | Call suggest() on O(1) constant function | Input: "def f(a,b): return a+b" | AI Suggestion contains "Time Complexity: O(1)" | O(1) stated correctly ✅ PASS — matches screenshot output
12 | ai_suggester.py — PEP8 analysis returned | Call suggest() on function named calculateSum (camelCase) | Input: def calculateSum(a,b): return a+b | AI Suggestion contains PEP8 warning about naming convention | PEP8 naming issue flagged ✅ PASS
13 | analyze.py — Analyze Code button triggers review | Click "Analyze Code" button after pasting code | Paste sample code, click button | Score panel appears with Score X/100, Issues Found section, AI Suggestions | Score 90/100 displayed ✅ PASS — verified in screenshot
14 | analyze.py — Your Code vs Corrected Code panels | Submit code with issues; check output section | Input: import os + def calculate_sum with x=10 | Left blue panel shows original code; right green panel shows corrected version (import os and x=10 removed) | Side-by-side panels correct ✅ PASS — verified in screenshot
15 | history.py — Previous analyses listed | Open History page after completing 2+ analyses | Navigate to /history URL | All previous submissions shown with code preview, score badge, and timestamp | 5 history entries displayed ✅ PASS — verified in history screenshot